## Sheet1
Poornima College of Engineering Department of Information Technology Product Backlog (Project-II: 2018-19)
Epic | Sprint | User Story Role | User Story name | Story Details | Task Items | Analyst/Prep work | Dev. Est | QA | User Story hours
Poornima Payments | 1 | DevTeam | Documentation of application | The dev. team will create the preliminary documents of the application | 1. Create synopsis that defines an abstract of all the requirements required for the system. 2. Create SRS that is the Software Requirement Specification document which specifies detailed functionalities of the system. 3. Mention the feasibility study of the system that tests theTechnical,Operational and Economical feasibility. 4. The dev. team will also specify the functional/non-functional requirements, technical requirements, system features of the system. | 10 | 18 | 4 | 32
Poornima Payments | 2 | End User | Creating registration page. | As an end user I should be able to register to the application by entering necessary details | 1. Create a registration form for the user (with fields Full name, phone number, e-mail id, password) . The information is added in the user database table (login table). | 5 | 5 | 3 | 13
Poornima Payments | 2 | End User | Creating login page. | As an end user I should be able to sign in with the information I registered with. | 1. Create a sign in page(with fields Email-id, password) where user can login using email id and password. 2. Redirect to login page again if email id or password is wrong. 3. Send an e-mail to registered email id if password is forgotten. | 4 | 5 | 4 | 13
Poornima Payments | 3 | Admin | Creating database of application. | The admin has to create databases that store information entered by the user. Information has to be retirved when required | 1. Create a database that consists of 3 tables which are user table, payment table, feedback table. 2. The user login table consists of fields ( email-id, name, mobile number and password ) 3. The passbook table consists of fields ( email-id, balance, transacton_details) 4. The feedback table consists of the comment column ( User ID: foreign key) | 5 | 15 | 3 | 23
Poornima Payments | 4 | End User | Creating GUI of the homepage. | As an end user I will be able to view the home page and exploit various other options present there. | 1. Design the Graphical User Interface of the home page and also create a Navigation bar. 2. Home-Page consist of following buttons (add money,pay,accept money, passbook). | 4 | 9 | 2 | 15
Poornima Payments | 4 | End User | Creating Navigation tab. | As an end user I will be able to go to the 'Navigation bar' and it explores the application | 1.Create a navigation bar named as 'Profile' which contains details about the user. 2. Inside navigation bar it will have several buttons(like 'QR Code', balance , settings , rate us , help and support , FAQ's , share , about us ,Logout) | 4 | 15 | 2 | 21
Poornima Payments | 5 | End User | Creating pay button | As an end user I will be able to pay the money by selecting the pay button | 1. Pay button contains two methods of payments.{ Create a textbox where payee can pay the money by using recipient's registered number on application and Create a scanner where payee can pay the money by scanning recipient's QR code.} | 4 | 22 | 4 | 30
Poornima Payments | 6 | End User | Creating accept money button | As an end user I will able to receive the money by the payee by selecting the accept money button. | 1. Create a button 'Accept Money' which contains QR code of the users profile which is used to receive the money by the payee. | 4 | 20 | 4 | 28
Poornima Payments | 7 | End User | Creating add money button | As an end user I will be able to add my money by bank by the selecting add money button | 1.Create a textbox which is used to enter the amount to add money in the wallet. | 4 | 12 | 4 | 20
Poornima Payments | 7 | End User | Creating passbook button | As an end user I will be able to check my balance by selecting the passbook button. | 1. Create a 'Check balance' button where user can see their wallet balance. 2. Create a 'Transaction' button which contains the all details of the transaction done by the user. | 3 | 10 | 3 | 16
Poornima Payments | 7 | End User | Creating feedback box | As an end user I should be able to provide feedback and register the complaint. | 1. Create a feedback form for each user and add feedback information to the database for review. | 2 | 3 | 2 | 7
Total Hours | [5 empty] | 49 | 134 | 35 | 218
Signature (Project Guide) |  |  |  |  | Signature ( Scrum Master) |  | Signature (Project Coordinator)