## Template cum 7ITPR Gantt Chart
POORNIMA COLLEGE OF ENGINEERING DEPARTMENT OF INFORMATION TECHNOLOGY SESSION 2017-18: ODD SEMESTER PROJECT - I (7ITPR) - GANTT CHART
PROJECT - I SCHEDULE |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2018-07-09 | 2018-07-10 | Inaugural Presentation | 2
2018-07-17 | 2018-07-19 | Group Finalization | 3
2018-07-19 | 2018-07-21 | Selection of Category of project | 3
2018-07-21 | 2018-07-23 | Problem identification and definition | 3
2018-07-23 | 2018-07-24 | Guide’s Acceptance and Project Approval | 2
2018-07-24 | 2018-07-26 | Literature Survey of Problem | 3
2018-07-26 | 2018-07-27 | Synopsis Submission | 2
2018-07-27 | 2018-08-14 | Synopsis Presentation | 19
2018-07-31 | 2018-08-13 | Project Presentation | 14
2018-08-08 | 2018-08-20 | Requirement Analysis & Planning Submission | 15
2018-08-20 | 2018-08-27 | System Design Document Submission | 8
2018-08-27 | 2018-09-14 | Source code development (Phase - I) | 19
2018-09-14 | 2018-09-21 | Unit Testing (Phase - I) | 8
2018-09-28 | 2018-10-17 | Source code development (Phase - II) | 20
2018-10-18 | 2018-10-28 | Unit Test (Phase-II), Code Review & Integration Testing | 11
2018-10-29 | 2018-11-02 | Project Report Submission | 5